## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Yonas Getachew Dejene | Project Lead | y.dejene@alustudent.com
Derick Gatete | Project Lead | d.gatete@alustudent.com
Habibllah Ayodele | Project Lead | h.ayodele@alustudent.com
Brian Kiki K. Nakuwa | Project Lead | b.nakuwa@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Design ERD, Map Database to JSON schema, Build API's (Get request), Creating JSON instances for each entity. | Yonas Dejene | 2026-01-26 | Completed | Yes | Have completed the ERD, JSON Instances created as well,Working on the API's (Get request).
| Write the SQL instructions, Build API's (Post, Put request) | Derick Gatete | 2026-01-26 | Completed | Yes | Created SQL instructions to create the DB and Entity Tables with their respective attributes. Working on the API's (post, put)
| Developing the json schemas and documentting some project sections. | Brian Nakuwa | 2026-01-26 | Completed | Yes | Created the json schemas and documented some project sections.
| Documentation and writing the SQL codes to run the database | Habibllah Ayodele | 2026-01-26 | Completed | Yes | Completely documented everything and also completed the sql instructions
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2026-01-19 | Debriefing about the first part of the project. | Derick | Derick Brian Yonas Habib | Looked at the xml file. Identifying the core entities and attributes. | Everyone get's a chance to do research and read about how we can approach the project.
2026-01-20 | Dissecting the project into specific tasks and delagating them to the team members. | Brian | Derick Brian Yonas Habib | Dissection of the project and task delegation. | Each and every member is expected to focus on the delegated task(s) and get it done within the provided proejct time frame.
2026-01-21 | Following up with our tasks and updating our progress with each other. | Habib | Derick Brian Yonas Habib | First Draft of ERD complete. It was over engineered and complex for the project given. | Simplify the ERD and prepare the final draft. Move on quick to create the sql instructions and creating the JSON Schemas.
2026-01-22 | Reinforcing the previous meeting's agenda and providing clarrifcations on team members' inquries. | Brian | Derick Brian Yonas Habib | Reinforcement of the previous meeting's agenda and opening room for project-related inquiries. | Members should continue progressing through their allocated task(s) to ensure timely completion.
2026-01-26 | Following up and checking that everone completed their allocated tasks. Review our work with regards to the rubric requirements. | Yonas | Derick Brian Yonas Habib | Polish the README file. Update the task status on the Scrum board. Submit the deliverables. | Stay active and ancticipate the opening of the following phases of the project.